## 00_README
CI CARIBBEAN
Lean Six Sigma Project Tracker
Continuous Improvement Program ¦ Caribbean Region
Version | 2.0
Date | 2026-05-11
Owner | CI Caribbean — Regional Continuous Improvement
Scope | 9 operations: PR, HT, RD, SXM, STT, ATG, DMA, SR, GF ¦ 325 employees
Currency | USD (all financial figures consolidated)
WORKBOOK CONTENTS
Sheet | Purpose
00_README | This page — overview, instructions, version log
01_Projects | Master project register: 6 Cohort-1 GB projects + 5 ongoing Black Belt projects (cross-site).
02_Belts | Registry of trained personnel (Yellow / Green / Black / MBB). Auto-counts projects.
03_Training | Training session log. Each row = one cohort or wave.
04_Benefits | Monthly realized savings by project. Feeds Finance validation.
05_Ideas | Ideas hopper. Where every employee suggestion lives before becoming a project.
06_Lookups | Dropdown source values. Edit here to update all dropdowns regionally.
HOW TO USE
1. Each project owner updates 01_Projects weekly: KPI Current, % Complete, Phase, Status.
2. When training is delivered, log the session in 03_Training and add each trainee to 02_Belts.
3. As savings are realized, add monthly rows to 04_Benefits with Finance validation.
4. Any employee idea goes to 05_Ideas and is reviewed by CI Council monthly.
5. Site dropdowns, pillars, statuses, and currencies are configured in 06_Lookups.
6. File is the single source for the Power BI dashboard — refreshed daily at 05:00 AST.
STATUS COLOR LEGEND
Green | On track — KPI achievement >70% or closed with benefits
Amber | At risk — slight schedule slip or moderate KPI progress
Red | Off track — overdue or KPI <40%
Grey | Cancelled or On-Hold
Formula | Formula cell — calculated automatically. Do NOT type into these cells; their values update when you change inputs.
WHAT'S NEW IN v2.0 | • Added 5 Black Belt projects across PR, RD, SR, and cross-Caribbean. • Registered 3 Black Belts. • Formula cells now highlighted in teal. • Cycle Time formula updated to show elapsed days for active projects.
ARGOS © Copyright 2026

## 01_Projects
PROJECT REGISTER
Master tracker of all CI projects across 9 Caribbean operations.
Project_ID | Project_Name | Site | Department | Strategic_Pillar | Project_Type | Problem_Statement | Goal_Statement | KPI_Name | KPI_Unit | KPI_Baseline | KPI_Target | KPI_Current | % KPI Achieved | DMAIC_Phase | Status | % Complete | Belt_Owner | Belt_Level | Sponsor | Champion | Start_Date | Planned_Close_Date | Actual_Close_Date | Cycle_Time_Days | Hard_Savings_USD | Cost_Avoidance_USD | Total_Benefits_USD | Finance_Validated | Cancellation_Reason | Risks_Issues | Lessons_Learned | Last_Updated
CI-PR-2026-001 | Reduce Kiln 2 Specific Heat Consumption | PR | Production – Kiln | Cost | DMAIC Green Belt | Kiln 2 SHC is 3,850 MJ/t vs benchmark 3,650 MJ/t — annualized gap ~$420K at current fuel cost. | Reduce Kiln 2 SHC from 3,850 to 3,700 MJ/t by 31-Mar-2026 (gain ≥$185K annualized). | Specific Heat Consumption | MJ/t clinker | 3850 | 3700 | 3695 | 103.3% | Closed | Closed-Benefits | 100% | María González | Green Belt | José Rodríguez | Plant Manager PR | 2025-10-01 | 2026-03-31 | 2026-03-28 | 178 | 185000 | 0 | 185000 | Yes |  |  | False air >12% was the root cause. Calibrated burner secondary air. Control plan: weekly false-air audit. Replicable to Kiln 1. | 2026-05-11
CI-RD-2026-002 | Optimize Cement Mill 1 Throughput | RD | Production – Grinding | Cost | DMAIC Green Belt | Cement Mill 1 throughput is 95 t/h vs design 110 t/h. Bottleneck for OPC production. Gap ~$280K/yr. | Increase Mill 1 throughput from 95 to 105 t/h by 31-Aug-2026 (≥$150K annualized). | Mill Throughput | t/h | 95 | 105 | 99 | 40% | Improve | Active | 65% | Rafael Núñez | Green Belt | Luisa Thomas | Plant Manager RD | 2026-01-15 | 2026-08-31 |  | 116 | 0 | 0 | 0 | Pending |  | Grinding aid dosing system may need replacement (capex pending). |  | 2026-05-11
CI-PR-2026-003 | Reduce Truck Loading Cycle Time at PR Terminal | PR | Logistics | Delivery | DMAIC Green Belt | Average truck loading cycle is 38 min vs target 25 min, causing customer delays and overtime. | Reduce truck loading cycle from 38 to 28 min by 30-Sep-2026 (≥$95K/yr in OT and capacity). | Avg Truck Loading Cycle Time | minutes | 38 | 28 | 34 | 40% | Analyze | Active | 40% | Sarah Williams | Green Belt | Andrés Pierre | Logistics Director Caribbean | 2026-02-01 | 2026-09-30 |  | 99 | 0 | 0 | 0 | Pending |  | Driver shortage may slow data collection. |  | 2026-05-11
CI-HT-2026-004 | Reduce Packaging Defects (Torn Bags) at HT | HT | Packaging | Quality | DMAIC Green Belt | Torn bag rate 2.8% vs target 1.0%. Returns cost ~$120K/yr plus reputational impact. | Reduce torn bag rate from 2.8% to 1.2% by 30-Jun-2026. | Torn Bag Rate | % | 2.8 | 1.2 | 2.8 | -0% | Define | Cancelled | 10% | Jean-Baptiste Pierre | Green Belt | Plant Manager HT | Quality Director Caribbean | 2026-01-20 | 2026-06-30 | 2026-03-15 | 54 | 0 | 0 | 0 | N/A | Scope too broad |  | Scope spanned 3 distinct failure modes. Recharter as 3 separate Kaizen events. | 2026-05-11
CI-SR-2026-005 | Reduce Unplanned Stops on Raw Mill SR | SR | Maintenance | Cost | DMAIC Green Belt | Raw mill unplanned stops avg 14 hrs/month vs target 4 hrs. Lost production ~$310K/yr. | Reduce raw mill unplanned stops from 14 to 6 hrs/month by 30-Jun-2026. | Unplanned Stops | hrs/month | 14 | 6 | 14 | -0% | Measure | Cancelled | 15% | Akira Tanaka | Green Belt | Plant Manager SR | Maintenance Director Caribbean | 2026-01-15 | 2026-06-30 | 2026-04-01 | 76 | 0 | 0 | 0 | N/A | Sponsor disengaged |  | No reliable downtime data system; needs IoT/CMMS investment before re-attempt. | 2026-05-11
CI-ATG-2026-006 | Improve Spare Parts Inventory Turnover ATG | ATG | Supply Chain | Cost | DMAIC Green Belt | Inventory turnover at 1.2 vs benchmark 3.0. Tied-up capital ~$1.4M. | Improve turnover from 1.2 to 2.0 by 31-Aug-2026 (free ~$400K working capital). | Inventory Turnover | turns/yr | 1.2 | 2 | 1.2 | 0% | Define | Cancelled | 5% | Marcus Brown | Green Belt | Supply Chain Director | Plant Manager ATG | 2026-02-01 | 2026-08-31 | 2026-03-25 | 52 | 0 | 0 | 0 | N/A | Solution already known (should be Just-Do-It) |  | Was really a "review and obsolete-flag" task, not a DMAIC. Re-launched as Just-Do-It under Supply Chain. | 2026-05-11
CI-PR-2026-007 | Increase Thermal Substitution Rate (TSR) — PR Plant | PR | Production – Kiln | Environment | DMAIC Black Belt | PR plant TSR is 12% vs Caribbean target 25% and global best 60%+. Annualized fuel cost gap ~$1.2M plus CO2 reduction opportunity. | Increase PR plant TSR from 12% to 22% by 31-Dec-2026 (≥$650K annualized fuel savings + ~28kt CO2 avoided). | Thermal Substitution Rate | % | 12 | 22 | 15 | 30% | Improve | Active | 55% | Carolina Restrepo | Black Belt | Regional Operations Director | Plant Manager PR | 2025-11-01 | 2026-12-31 |  | 191 | 0 | 0 | 0 | Pending |  | Regulatory approval pending for new fuel mix; alt-fuel supplier qualification in progress. |  | 2026-05-11
CI-RD-2026-008 | Clinker Factor Reduction — RD Plant | RD | Production – Process | Environment | DMAIC Black Belt | Clinker factor at 0.78 vs benchmark 0.68. Each 1% reduction ≈ $200K/yr and ~40kt CO2. | Reduce clinker factor from 0.78 to 0.72 by 30-Nov-2026 (≥$580K annualized + carbon credit eligibility). | Clinker Factor | ratio | 0.78 | 0.72 | 0.76 | 33.33% | Analyze | Active | 45% | Patricia Mendoza | Black Belt | Regional Quality Director | Plant Manager RD | 2026-01-08 | 2026-11-30 |  | 123 | 0 | 0 | 0 | Pending |  | SCM (pozzolan) supplier qualification ongoing; cement standard variations across export markets. |  | 2026-05-11
CI-CAR-2026-009 | Marine Logistics Optimization — Cross-Caribbean | PR | Regional Logistics | Cost | DMAIC Black Belt | Vessel charter cost up 18% YoY; avg port turnaround 32 hrs vs 22 hr benchmark; demurrage exposure $480K/yr. Spans PR, STT, ATG, DMA, SXM. | Reduce inter-island shipping cost per ton by 12% by 31-Mar-2027 (≥$1.1M annualized across 5 sites). | Shipping Cost per Ton | USD/t | 24.5 | 21.5 | 23.8 | 23.33% | Measure | Active | 25% | Diana Rojas | Black Belt | VP Caribbean Logistics | Logistics Director Caribbean | 2026-02-15 | 2027-03-31 |  | 85 | 0 | 0 | 0 | Pending |  | Hurricane season Jun-Nov may distort data; multi-site governance complexity. |  | 2026-05-11
CI-SR-2026-010 | Predictive Maintenance Deployment — Critical Equipment | SR | Maintenance | Cost | DMAIC Black Belt | Reactive maintenance ratio 48% vs target <30%. Avg unplanned downtime cost $180K/incident. Pilot at SR, scalable across region. | Reduce reactive maintenance ratio from 48% to 32% by 31-Dec-2026 at SR (≥$420K annualized + replicable playbook for 8 other sites). | Reactive Maintenance Ratio | % | 48 | 32 | 44 | 25% | Improve | Active | 60% | Carolina Restrepo | Black Belt | Regional Operations Director | Plant Manager SR | 2025-12-01 | 2026-12-31 |  | 161 | 0 | 0 | 0 | Pending |  | IoT sensor installation requires shutdown windows; CMMS data quality issues persist. |  | 2026-05-11
CI-RD-2026-011 | Cement Quality Variability Reduction — Cross-Site | RD | Quality | Quality | DMAIC Black Belt | 28d compressive strength σ=2.8 MPa vs target 1.5 MPa. Customer complaints up 22% YoY across PR, RD, HT, GF. | Reduce 28d compressive strength σ from 2.8 to 1.8 MPa across 4 sites by 30-Jun-2027. | Compressive Strength σ (28d) | MPa | 2.8 | 1.8 | 2.8 | -0% | Define | Active | 15% | Patricia Mendoza | Black Belt | VP Caribbean Quality | Quality Director Caribbean | 2026-04-01 | 2027-06-30 |  | 40 | 0 | 0 | 0 | Pending |  | Standardization of lab test methods needed first; multi-country lab coordination. |  | 2026-05-11
Formulas:
Cycle_Time_Days = IF([Actual_Close_Date]="",TODAY()-[Start_Date],[Actual_Close_Date]-[Start_Date])

## 02_Belts
BELT REGISTRY
Registry of all personnel trained or certified. Auto-counts their projects.
Employee_ID | Full_Name | Email | Site | Department | Role | Belt_Level | Training_Date | Certification_Date | Cohort_Code | Active_Projects | Closed_Benefits_Projects | Cancelled_Projects | Total_Savings_Delivered_USD | Status | Notes
EMP-PR-0214 | María González | mgonzalez@argos.com.do | PR | Production – Kiln | Process Engineer | Green Belt | 2026-01-15 | 2026-03-28 | GB-C1-2026 | 0 | 1 | 0 | 185000 | Active | Top performer Cohort 1
EMP-RD-0118 | Rafael Núñez | rnunez@argos.com.do | RD | Production – Grinding | Production Supervisor | Green Belt | 2026-01-15 |  | GB-C1-2026 | 1 | 0 | 0 | 0 | Active
EMP-PR-0331 | Sarah Williams | swilliams@argos.com | PR | Logistics | Logistics Supervisor | Green Belt | 2026-01-15 |  | GB-C1-2026 | 1 | 0 | 0 | 0 | Active
EMP-HT-0089 | Jean-Baptiste Pierre | jpierre@argos.com.ht | HT | Packaging | Packaging Lead | Green Belt | 2026-01-15 |  | GB-C1-2026 | 0 | 0 | 1 | 0 | Active | Project cancelled but completed training
EMP-SR-0042 | Akira Tanaka | atanaka@argos.com.sr | SR | Maintenance | Maintenance Engineer | Green Belt | 2026-01-15 |  | GB-C1-2026 | 0 | 0 | 1 | 0 | Active | Project cancelled but completed training
EMP-ATG-0007 | Marcus Brown | mbrown@argos.com.ag | ATG | Supply Chain | Inventory Analyst | Green Belt | 2026-01-15 |  | GB-C1-2026 | 0 | 0 | 1 | 0 | Active | Project cancelled but completed training
EMP-CAR-0001 | Carolina Restrepo | crestrepo@argos.com.co | PR | Regional CI | Regional Black Belt | Black Belt | 2024-06-15 | 2024-12-10 | BB-Argos-2024 | 2 | 0 | 0 | 0 | Active | Leads 2 active BB projects (TSR PR, PdM SR). Internal MBB candidate.
EMP-RD-0007 | Patricia Mendoza | pmendoza@argos.com.do | RD | Process & Quality | Black Belt | Black Belt | 2024-08-20 | 2025-02-14 | BB-Argos-2024 | 2 | 0 | 0 | 0 | Active | Leads Clinker Factor RD and Quality cross-site BB projects.
EMP-PR-0019 | Diana Rojas | drojas@argos.com | PR | Logistics | Black Belt | Black Belt | 2025-01-13 | 2025-07-22 | BB-Argos-2025 | 1 | 0 | 0 | 0 | Active | Leads Marine Logistics cross-Caribbean BB project.

## 03_Training
TRAINING LOG
Record of every training session delivered (Yellow / Green / Black Belt and Kaizen).
Training_ID | Date_Start | Date_End | Program_Type | Cohort_Code | Modality | Language | Host_Site | Instructor | Instructor_Type | Delivered_Hours | Attendees_Planned | Attendees_Actual | Attendance_% | Pass_Rate_% | Avg_Satisfaction | Cost_USD | Notes
TR-2026-001 | 2026-01-12 | 2026-01-16 | Green Belt | GB-C1-2026 | In-person | EN/ES | PR | Carlos Vargas (MBB) | External | 40 | 8 | 6 | 75% | 100% | 4.6 | 18000 | First Green Belt cohort. 1 closed with benefits, 3 cancelled. Lessons captured for Cohort 2.
TR-2026-002 | 2026-02-20 | 2026-02-20 | Yellow Belt | YB-Wave1-2026 | Virtual | EN/ES/FR | All sites | María González (GB) | Internal | 4 | 60 | 48 | 80% | 96% | 4.4 | 1200 | First Yellow Belt wave post Green Belt graduation.
TR-2026-003 | 2026-04-15 | 2026-04-15 | Yellow Belt | YB-Wave2-2026 | Virtual | EN/FR | All sites | Sarah Williams (GB) | Internal | 4 | 40 | 32 | 80% | 94% | 4.5 | 1000 | Second Yellow Belt wave focused on East Caribbean.

## 04_Benefits
MONTHLY BENEFITS REALIZATION
One row per project × month × benefit category. Feeds run-rate and Finance validation.
Benefit_ID | Project_ID | Month_Year | Category | Amount_USD | Plan_or_Actual | Validated_By_Finance | Validation_Date | Notes | Total Validated (Actual) | 30834
BEN-2026-001 | CI-PR-2026-001 | 2026-04-01 | Hard | 15417 | Actual | Yes | 2026-04-01 | Kiln 2 SHC reduction — month 1 of 12 | Total Pipeline (Plan) | 154170
BEN-2026-002 | CI-PR-2026-001 | 2026-05-01 | Hard | 15417 | Actual | Yes | 2026-05-01 | Kiln 2 SHC reduction — month 2 of 12 | Total Annualized Forecast | 185004
BEN-2026-003 | CI-PR-2026-001 | 2026-06-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 3 of 12
BEN-2026-004 | CI-PR-2026-001 | 2026-07-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 4 of 12
BEN-2026-005 | CI-PR-2026-001 | 2026-08-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 5 of 12
BEN-2026-006 | CI-PR-2026-001 | 2026-09-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 6 of 12
BEN-2026-007 | CI-PR-2026-001 | 2026-10-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 7 of 12
BEN-2026-008 | CI-PR-2026-001 | 2026-11-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 8 of 12
BEN-2026-009 | CI-PR-2026-001 | 2026-12-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 9 of 12
BEN-2026-010 | CI-PR-2026-001 | 2027-01-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 10 of 12
BEN-2026-011 | CI-PR-2026-001 | 2027-02-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 11 of 12
BEN-2026-012 | CI-PR-2026-001 | 2027-03-01 | Hard | 15417 | Plan | Pending |  | Kiln 2 SHC reduction — month 12 of 12

## 05_Ideas
IDEAS HOPPER
All employee suggestions and improvement ideas. Reviewed monthly by CI Council.
Idea_ID | Date_Submitted | Submitter | Site | Title | Description | Strategic_Pillar | Estimated_Impact_USD | Impact_Score | Effort_Level | Priority_Score | Quadrant | Status | Decision_Date | Linked_Project_ID | Notes
IDEA-2026-001 | 2026-02-05 | L. Domínguez | PR | LED retrofit in warehouse | Replace HID lights in clinker warehouse with LED. Estimated $35K/yr energy savings. | Cost | 35000 | 4 | Low | 4 | Quick Win | Approved | 2026-02-20 |  | Converted to Just-Do-It under Maintenance.
IDEA-2026-002 | 2026-02-10 | F. Joseph | HT | Reduce conveyor belt wear at HT | Belt life is 6 months vs OEM 18 months. Suspect misalignment + dust ingress. | Cost | 80000 | 4 | Med | 1.3333 | Major Project | Under Review |  |  | Candidate for Green Belt Cohort 2.
IDEA-2026-003 | 2026-02-15 | K. Duarte | RD | Standardize PPE inspection on shift change | Reduce near-misses related to gloves and respirator fit. | Safety | 0 | 3 | Low | 3 | Fill-in | Approved | 2026-02-28 |  | Implemented as one-point lesson.
IDEA-2026-004 | 2026-03-01 | R. Sánchez | PR | Alternative fuel: tire chips co-processing | Pilot 5% TSR using locally-sourced tire chips. Est savings $250K/yr if scaled. | Environment | 250000 | 5 | High | 1 | Major Project | Under Review |  |  | Needs regulatory check + capex for feed system.
IDEA-2026-005 | 2026-03-07 | A. Pierre | GF | Digital truck dispatch QR codes | Replace paper manifests with QR. Speeds loading, reduces errors. | Delivery | 45000 | 4 | Low | 4 | Quick Win | Approved | 2026-03-20 |  | IT scoping pilot for GF and SR.
IDEA-2026-006 | 2026-03-12 | M. Allen | STT | Improve marine vessel turnaround at STT terminal | Avg vessel turnaround 36 hrs vs target 24. Demurrage exposure ~$120K/yr. | Delivery | 120000 | 5 | Med | 1.6667 | Major Project | New |  |  | Pending CI Council review April.
IDEA-2026-007 | 2026-03-18 | J. López | RD | Reduce dust emissions raw mill stack | Stack opacity reading drifts above limit during startup. | Environment | 0 | 3 | Med | 1 | Thankless | Under Review |  |  | Regulatory priority — environmental.
IDEA-2026-008 | 2026-03-25 | D. Charles | DMA | Bag silo level sensors | 3 unplanned overflows in Q1. Install ultrasonic level sensors. | Quality | 25000 | 3 | Low | 3 | Fill-in | Approved | 2026-04-05 |  | Approved capex.
IDEA-2026-009 | 2026-04-02 | I. Hassan | SR | CMMS data quality cleanup | Work order data is poor; foundation for predictive maintenance project. | Cost | 0 | 4 | High | 0.8 | Thankless | New |  |  | Pre-requisite for SR maintenance Green Belt re-attempt.
IDEA-2026-010 | 2026-04-12 | P. Singh | SXM | Pre-blend silo homogenization | LSF variability ±15 vs target ±5. Affects clinker quality. | Quality | 90000 | 4 | Med | 1.3333 | Major Project | Under Review |  |  | Candidate Green Belt Cohort 2 or Black Belt.

## 06_Lookups
Lookups & Dropdown Sources
Edit values here to update dropdowns across all sheets.
SITES |  |  |  |  | STRATEGIC PILLARS | PROJECT TYPES | DMAIC PHASES | PROJECT STATUS | BELT LEVELS | CANCELLATION REASONS | YES/NO
Site_Code | Country | Region | Currency | Timezone | Pillar | Type | Phase | Status | Belt_Level | Reason | Value
PR | Puerto Rico | Caribbean North | USD | America/Puerto_Rico | Safety | DMAIC Green Belt | Define | Proposed | White Belt | Scope too broad | Yes
HT | Haiti | Caribbean North | USD | America/Port-au-Prince | Quality | DMAIC Black Belt | Measure | Active | Yellow Belt | Sponsor disengaged | No
RD | Dominican Republic | Caribbean North | USD | America/Santo_Domingo | Cost | Kaizen Event | Analyze | On-Hold | Green Belt | Resources reassigned | Pending
SXM | Sint Maarten | Caribbean East | USD | America/Lower_Princes | Delivery | Just-Do-It | Improve | Cancelled | Black Belt | Data not available | N/A
STT | St Thomas (USVI) | Caribbean East | USD | America/St_Thomas | People | A3 | Control | Closed-Benefits | Master Black Belt | Solution already known (should be Just-Do-It)
ATG | Antigua | Caribbean East | USD | America/Antigua | Environment |  | Closed | Closed-NoBenefits |  | Strategic priority changed
DMA | Dominica | Caribbean East | USD | America/Dominica |  |  | N/A |  |  | Capex required not approved
SR | Suriname | Caribbean South | USD | America/Paramaribo | [5 empty] | Belt left the company
GF | French Guiana | Caribbean South | USD | America/Cayenne
CONFIG PARAMETERS
Parameter | Value
Current_FY | 2026
FY_Start_Date | 2026-01-01
Annual_Savings_Target_USD | 1000000
Total_Workforce | 325
Training_Target_Hours_Per_Employee | 8
RAG_KPI_Green_Threshold | 0.7
RAG_KPI_Amber_Threshold | 0.4
Schedule_Variance_Amber_Days | 0
Schedule_Variance_Red_Days | -14
ARGOS © Copyright 2026